## Blad1
Task name | Deadline | Responsible | Status | Notes
Personal Learning Goals | 2025-12-19 | Everyone | In progress | Everyone works on it individually
Team Learning Goals | 2025-12-19 | Everyone | In progress
Schedule meeting case-owner and practioner |  | Gino | In progress | Julia checks work agenda and let's Gino know which dates to send
Define the roles and responsibilties | 2025-12-19 | Everyone | Not started yet
Report outline | 2025-12-19 | Everyone | Not started yet
First Interim Report | 2026-01-30
Receive Feedback on First Interim Report | 2026-02-06
First Practitioner Meeting | 2026-03-06
Second Interim Report | 2026-03-20
Receive Feedback on Second Interim Report | 2026-03-27
Second Practitioner Meeting | 2026-04-17
Third Interim Report (GO/NO GO) | 2026-05-08
Receive Feedback on Third Interim Report | 2026-05-15
Third Practitioner Meeting | 2026-06-05
Final Report Submission | 2026-06-19
Personal Reflection Submission | 2026-06-19
Team Reflection Submission | 2026-06-19
Jupyter Notebook/Python Scripts Submission | 2026-06-19
Graduation Presentation Slides | 2026-06-25
Graduation - Applications of Data & AI 🎉 | 2026-07-03